## Sheet1
Project Name | PHPTravels Website
Purpose: To ensure that the work product meets specifications for performance, defects must be tracked and fixed. These defects may arise from any Phase, but the majority will arise in the Testing Phase and must be properly captured and tracked through resolution. This form will allow documentation of test defects that must be corrected prior to project completion. Also, this form makes it easier to monitor status of the defect correction progress. This form may be used by any member of the software development team.
Defect No. | Date Created | Created By | Defect Description | Lifecycle Phase | Priority
1 | 30/10/2022 | Shruthi Suresh | Home link not present in Customer dashboard | Testing | H
2 | 2022-03-11 | Shruthi Suresh | Status change not correctly updated in the invoice displayed in Admin Bookings | Testing | H
3 | 2022-04-11 | Shruthi Suresh | Flight module not found in Supplier dashboard | Testing | H
4 | 2022-04-11 | Shruthi Suresh | Visa module not found in Supplier dashboard | Testing | H
5 | 2022-04-11 | Shruthi Suresh | Tours module not found in Supplier dashboard | Testing | H
6 | 2022-04-11 | Shruthi Suresh | Booking link in Supplier dashboard is redirecting to a page which is showing Error | Testing | M